## Construction Dashboard
Sr No | Stage | Task | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Cost (Cr) | Time (Days) | Cost Weight | Time Weight
1 | DPR | Inception report | Consultant | Client | PMC | Govt | 0.08 | 15 | 0.003498 | 0.010316
2 | DPR | Feasibility study | Consultant | Client | Survey | PMC | 0.3 | 30 | 0.013118 | 0.020633
3 | DPR | Traffic survey | Consultant | Client | Experts | PMC | 0.15 | 20 | 0.0065588 | 0.013755
4 | DPR | Topographic survey | Survey Team | Consultant | Contractor | Client | 0.2 | 25 | 0.0087451 | 0.017194
5 | DPR | Geotech investigation | Consultant | Client | Lab | PMC | 0.35 | 30 | 0.015304 | 0.020633
6 | DPR | LA Stage I | Consultant | Client | Govt | PMC | 0.1 | 20 | 0.0043725 | 0.013755
7 | DPR | DPR preparation | Consultant | Client | AE | PMC | 0.8 | 45 | 0.03498 | 0.030949
8 | DPR | BOQ prep | Consultant | Client | AE | PMC | 0.12 | 15 | 0.005247 | 0.010316
9 | LA | LA-II | Consultant | Client | Govt | PMC | 0.2 | 30 | 0.0087451 | 0.020633
10 | LA | LA-III | Govt | Client | Consultant | PMC | 2.5 | 60 | 0.10931 | 0.041265
11 | LA | LA-IV | Govt | Client | Consultant | Contractor | 1.8 | 90 | 0.078706 | 0.061898
12 | Tender | Tender prep | Consultant | Client | PMC | Contractor | 0.1 | 15 | 0.0043725 | 0.010316
13 | Tender | Tender invite | Client | Client | Consultant | Public | 0.02 | 10 | 0.00087451 | 0.0068776
14 | Tender | Prequalification | Client | Client | Consultant | PMC | 0.03 | 15 | 0.0013118 | 0.010316
15 | Tender | Technical bid | Client | Client | Consultant | Bidders | 0.02 | 5 | 0.00087451 | 0.0034388
16 | Tender | Financial bid | Client | Client | Consultant | Bidders | 0.02 | 5 | 0.00087451 | 0.0034388
17 | Tender | LOA | Client | Client | Consultant | Contractor | 0.01 | 7 | 0.00043725 | 0.0048143
18 | Pre-Con | AE appointment | Client | Client | Consultant | Contractor | 0.3 | 15 | 0.013118 | 0.010316
19 | Pre-Con | Utility shifting | Contractor | Client | Govt | PMC | 1.5 | 60 | 0.065588 | 0.041265
20 | Pre-Con | Clearances | Govt | Client | Consultant | PMC | 0.5 | 90 | 0.021863 | 0.061898
21 | Pre-Con | Camp setup | Contractor | Contractor | PMC | Client | 2 | 30 | 0.087451 | 0.020633
22 | Design | Design submission | Contractor | Contractor | Consultant | Client | 0.15 | 20 | 0.0065588 | 0.013755
23 | Design | Proof checking | Consultant | Client | AE | Contractor | 0.08 | 15 | 0.003498 | 0.010316
24 | Design | AE review | AE | Client | Consultant | Contractor | 0.05 | 10 | 0.0021863 | 0.0068776
25 | Design | Approval | Client | Client | AE | Contractor | 0.02 | 7 | 0.00087451 | 0.0048143
26 | Construction | Earthwork | Contractor | Contractor | AE | Client | 1.2 | 60 | 0.05247 | 0.041265
27 | Construction | Subgrade | Contractor | Contractor | AE | PMC | 0.8 | 30 | 0.03498 | 0.020633
28 | Construction | GSB+WMM | Contractor | Contractor | AE | PMC | 1 | 40 | 0.043725 | 0.02751
29 | Construction | Pavement | Contractor | Contractor | AE | Client | 3 | 50 | 0.13118 | 0.034388
30 | Construction | Drainage | Contractor | Contractor | AE | PMC | 0.7 | 40 | 0.030608 | 0.02751
31 | Construction | Structures | Contractor | Contractor | AE | Client | 4 | 120 | 0.1749 | 0.082531
32 | Post | Testing | AE | Client | Consultant | Contractor | 0.2 | 20 | 0.0087451 | 0.013755
33 | Post | Final billing | Contractor | Client | Consultant | PMC | 0.05 | 30 | 0.0021863 | 0.020633
34 | Post | Handover | Contractor | Client | AE | Public | 0.02 | 15 | 0.00087451 | 0.010316
35 | Post | DLP | Contractor | Contractor | Client | PMC | 0.5 | 365 | 0.021863 | 0.25103